🚌

REALBUS SIMULATOR

Master Project Timeline & Implementation Plan

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Version 1.0   |   March 2026   |   For Internal Use Only

Developer: Solo (with AI assistance)   |   Target: iOS & Android

Engine: Unity 6.3 LTS   |   Language: C#   |   Maps: OpenStreetMap + Mapbox

| Metric | Detail |
| --- | --- |
| Total Project Duration | 18 Months (March 2026 → September 2027) |
| Development Phases | 8 Phases + Pre-Production |
| Primary Developer Machine | HP ProBook 450 G5 ¦ i7-8550U ¦ 16 GB RAM ¦ Kali Linux |
| Test Devices | Samsung Galaxy S20 (high-end) + Samsung A54 (mid-range) |
| IDE | VS Code + C# Dev Kit + Unity Extension |
| Version Control | Git + GitHub (private repository) |
| Target Launch | September 2027 — Google Play + Apple App Store |
| Total Budget (est.) | ~$0–$200 USD (free tools + optional paid assets) |

How to Use This Document

This is a living document. It is designed to be your single source of truth throughout the entire development lifecycle of RealBus Simulator. Every phase has explicit entry criteria (what must be true before you start), exit criteria (what must be true before you move on), deliverables (tangible outputs), tasks broken down to the individual action level, estimated time costs, tools required, and known risks.

Read each phase in order. Do not skip ahead. The phases are designed so that each one de-risks the next. Attempting Phase 4 without completing Phase 2 will result in rework and wasted time.

| Icon | Meaning |
| --- | --- |
| 📌 NOTE | Important information you must not overlook |
| ⚠️ WARNING | Common mistake that causes project failure or major rework |
| ✅ TIP | Best practice or time-saving advice |
| 🎯 MILESTONE | A formal checkpoint — stop, verify, then continue |
| 🔁 RECURRING | A task that repeats on a schedule throughout the project |

Master Schedule Overview

| Phase | Name | Start | End | Duration | Status |
| --- | --- | --- | --- | --- | --- |
| PRE-0 | Environment & Toolchain Setup | Week 1 | Week 2 | 2 weeks | 🟡 In Progress |
| PHASE 1 | Unity Project Setup & Architecture | Week 3 | Week 4 | 2 weeks | ⬜ Not Started |
| PHASE 2 | Bus Physics Core | Week 5 | Week 10 | 6 weeks | ⬜ Not Started |
| PHASE 3 | Real Map Integration | Week 11 | Week 16 | 6 weeks | ⬜ Not Started |
| PHASE 4 | Core Gameplay Loop | Week 17 | Week 24 | 8 weeks | ⬜ Not Started |
| PHASE 5 | Realism Systems | Week 25 | Week 34 | 10 weeks | ⬜ Not Started |
| PHASE 6 | Progression & Meta Systems | Week 35 | Week 42 | 8 weeks | ⬜ Not Started |
| PHASE 7 | Polish, Audio & UX | Week 43 | Week 50 | 8 weeks | ⬜ Not Started |
| PHASE 8 | QA, Beta & Launch | Week 51 | Week 72 | 22 weeks | ⬜ Not Started |

📌 NOTE: Unity 6.3 LTS is already installed (13.9 GB). Unity Hub is installed. This gives you a head start on PRE-0.

⚠️  WARNING: Your disk is 84.7% full (~36 GB free). You MUST free space before creating Unity projects. A full disk will corrupt builds mid-compilation.

PHASE 0: ENVIRONMENT & TOOLCHAIN SETUP   [ Week 1–2 | ~10–14 hours total ]

This phase has nothing to do with game code. It is infrastructure. Skipping or rushing it causes cascading problems throughout the entire project. Every hour spent here saves five hours later.

0.1 — Disk Space Management

⚠️  WARNING: You have ~36 GB free. Unity projects routinely grow to 10–20 GB. Android builds add another 3–5 GB. Mapbox cache adds 500 MB. You need at least 50 GB free before starting.

Tasks:

- Run disk usage audit to find what is consuming space

- Move large files (videos, ISOs, archives) to external drive or cloud storage

- Clean apt package cache: sudo apt clean && sudo apt autoremove

- Remove old Linux kernels: sudo apt remove --purge $(dpkg -l 'linux-image-*' | awk '/^ii/{print $2}' | grep -v $(uname -r))

- Clear Unity Hub download cache if it exists: ~/.local/share/unityhub/

- Verify you have at least 50 GB free before proceeding

✅ TIP: Use 'ncdu' to interactively browse disk usage: sudo apt install ncdu && ncdu /

0.2 — NVIDIA Driver Installation

⚠️  WARNING: Your NVIDIA GeForce 930MX shows driver: N/A — it is not functioning. Unity will run on your Intel UHD 620 which is significantly slower and may cause thermal throttling during long edit sessions.

Tasks:

- Check current driver state: nvidia-smi (expect 'command not found')

- Add non-free repository: sudo apt-add-repository non-free

- Update package list: sudo apt update

- Install NVIDIA driver: sudo apt install nvidia-driver

- Reboot: sudo reboot

- Verify driver loaded: nvidia-smi (should show GPU info and driver version)

- Configure Unity to use NVIDIA GPU via PRIME profiles: sudo prime-select nvidia

- Reboot again and verify: glxinfo | grep 'OpenGL renderer' (should show GeForce)

📌 NOTE: The 930MX is a Maxwell-era GPU with 2 GB VRAM. It is not fast but it is roughly 3–5× faster than the Intel UHD 620 for 3D rendering.

⚠️  WARNING: On Kali Linux, NVIDIA drivers can conflict with Wayland. If your desktop breaks after install, switch to X11 at the login screen (click the gear icon before logging in).

0.3 — System Dependencies

Tasks (run in order):

- Install JDK 11 (required for Android builds): sudo apt install openjdk-11-jdk

- Set JAVA_HOME: echo 'export JAVA_HOME=/usr/lib/jvm/java-11-openjdk-amd64' >> ~/.zshrc

- Install .NET SDK 8: sudo apt install dotnet-sdk-8.0

- Install Git: sudo apt install git (verify: git --version)

- Install Git LFS (for large Unity assets): sudo apt install git-lfs && git lfs install

- Install curl and wget: sudo apt install curl wget

- Apply all changes: source ~/.zshrc

- Verify all installs with --version checks on each tool

0.4 — VS Code Configuration for Unity

Tasks:

- Install C# Dev Kit extension: code --install-extension ms-dotnettools.csdevkit

- Install Unity extension: code --install-extension visualstudiotoolsforunity.vstuc

- Install Shader languages extension: code --install-extension slevesque.shader

- Install GitLens extension: code --install-extension eamodio.gitlens

- Install EditorConfig extension: code --install-extension editorconfig.editorconfig

- Create VS Code settings file at ~/.config/Code/User/settings.json with Unity-specific settings

- Set omnisharp.useModernNet to true in VS Code settings

✅ TIP: VS Code Unity integration requires the project to be opened at least once in Unity first so that .csproj files are generated. Do this in Phase 1.

0.5 — Git & Version Control Setup

⚠️  WARNING: Version control is NOT optional even for solo projects. A single bad script, corrupted prefab, or accidental scene overwrite can wipe hours of work. Git is your safety net.

Tasks:

- Create GitHub account if you do not have one (free at github.com)

- Create a new PRIVATE repository named 'realbus-simulator'

- Configure Git identity: git config --global user.name 'Your Name' && git config --global user.email 'you@email.com'

- Generate SSH key for GitHub: ssh-keygen -t ed25519 -C 'you@email.com'

- Add SSH key to GitHub account settings

- Create .gitignore using Unity's official template (search 'Unity .gitignore' on gitignore.io)

- Configure Git LFS for Unity binary files: git lfs track '*.png' '*.jpg' '*.fbx' '*.wav' '*.mp3' '*.asset' '*.prefab' '*.unity' '*.unitypackage'

📌 NOTE: Unity .meta files MUST be committed to Git. Never add *.meta to .gitignore. Missing meta files cause GUIDs to regenerate and break all asset references.

0.6 — Android Device Setup

Tasks for Samsung S20:

- Go to Settings → About Phone → tap Build Number 7 times to enable Developer Options

- Go to Settings → Developer Options → enable USB Debugging

- Enable Stay Awake (prevents screen timeout during testing)

- Connect to laptop via USB — select 'File Transfer' mode on phone

- Verify: adb devices (should show device serial number, not 'unauthorized')

Tasks for Samsung A54 (repeat all above steps, then):

- On both devices, install 'CPU-Z' app to verify GPU and specs at runtime

- Set both phones to 'Never' for screen timeout in Developer Options

- Disable battery optimisation for Unity-built apps to prevent throttling during test sessions

0.7 — Account Registrations & API Keys

Tasks:

- Create Mapbox account at mapbox.com — free, no credit card required for free tier

- Navigate to Mapbox dashboard → Access Tokens → create a new token named 'RealBus-Dev'

- Copy the token to a secure local file: ~/.realbus_secrets (chmod 600 ~/.realbus_secrets)

- Create Unity Asset Store account at assetstore.unity.com

- Create PlayFab account at playfab.com (free tier for leaderboards and cloud saves)

- Bookmark: overpass-api.de (for OpenStreetMap queries, no account needed)

⚠️  WARNING: NEVER commit API keys to Git. Add .realbus_secrets and any Config.cs files containing keys to .gitignore immediately.

0.8 — Phase 0 Milestone Checklist

🎯 MILESTONE: Do not proceed to Phase 1 until every item below is checked.

| # | Checkpoint | Verify By | ✓ |
| --- | --- | --- | --- |
| 1 | Minimum 50 GB disk space free | df -h / | ☐ |
| 2 | NVIDIA driver loaded and recognised | nvidia-smi returns GPU info | ☐ |
| 3 | JDK 11 installed | java -version shows 11.x | ☐ |
| 4 | .NET SDK 8 installed | dotnet --version shows 8.x | ☐ |
| 5 | Git configured with SSH key | ssh -T git@github.com returns success | ☐ |
| 6 | Git LFS initialised | git lfs version succeeds | ☐ |
| 7 | Private GitHub repo created | Repo visible at github.com | ☐ |
| 8 | VS Code extensions installed (3) | code --list-extensions shows all 5 | ☐ |
| 9 | Both phones show in adb devices | adb devices lists 2 devices | ☐ |
| 10 | Mapbox token saved securely | Token file exists, not in Git | ☐ |

PHASE 1: UNITY PROJECT SETUP & ARCHITECTURE   [ Week 3–4 | ~20 hours ]

1.1 — Project Creation

Tasks:

- Open Unity Hub → New Project

- Select template: 3D (URP) — Universal Render Pipeline, NOT the legacy 3D template

- Name: RealBus-Simulator

- Location: Choose a directory with plenty of disk space (not /tmp)

- Click Create Project — wait for Unity to initialise (5–10 minutes)

- Once open, go to Edit → Project Settings → Editor → set External Script Editor to VS Code

- Open any C# script to trigger VS Code .csproj generation

- Close Unity, open project folder in VS Code, verify IntelliSense works on MonoBehaviour

⚠️  WARNING: Do NOT use the 3D (HDRP) template. HDRP is too heavy for mobile. URP is the correct choice for performance on Android devices.

1.2 — URP & Quality Settings

Tasks:

- Go to Edit → Project Settings → Quality → delete all quality levels except Low, Medium, High

- Create URP Asset for each quality level (Low/Med/High) in Assets/Settings/

- Configure Low URP asset: disable shadows, disable bloom, shadow distance 0, 1x render scale

- Configure Medium URP asset: enable shadows (64m), soft particles on, 1x render scale

- Configure High URP asset: shadows 150m, SSAO on, bloom on, 1x render scale

- Go to Edit → Project Settings → Player → Android → set minimum API level to 26 (Android 8.0)

- Set target API level to latest (34)

- Set Scripting Backend to IL2CPP (required for 64-bit Android — Google Play requirement)

- Set Target Architectures to ARM64 only

1.3 — Folder Structure

Create the following folder hierarchy inside Assets/ before writing a single script. Changing this later is painful.

| Folder Path | Contents |
| --- | --- |
| Assets/_Game/ | All game-specific content (underscore keeps it at top of list) |
| Assets/_Game/Scripts/ | All C# scripts, organised by system |
| Assets/_Game/Scripts/Bus/ | BusController, WheelManager, EngineSystem, etc. |
| Assets/_Game/Scripts/Map/ | MapStreamer, TileCache, OverpassQuery, etc. |
| Assets/_Game/Scripts/Passengers/ | PassengerAgent, StopManager, etc. |
| Assets/_Game/Scripts/Traffic/ | TrafficManager, AIVehicle, SignalController |
| Assets/_Game/Scripts/Weather/ | WeatherSystem, RainController, FogController |
| Assets/_Game/Scripts/UI/ | HUD, Menus, Minimap, ScoreDisplay |
| Assets/_Game/Scripts/Progression/ | XPSystem, UnlockManager, SaveManager |
| Assets/_Game/Prefabs/ | All prefabs — buses, passengers, stops, vehicles |
| Assets/_Game/Materials/ | URP-compatible materials only |
| Assets/_Game/Models/ | 3D models (FBX format) |
| Assets/_Game/Textures/ | All texture assets |
| Assets/_Game/Audio/ | Audio clips and FMOD assets |
| Assets/_Game/ScriptableObjects/ | Bus specs, city configs, route data |
| Assets/_Game/Scenes/ | All Unity scenes |
| Assets/ThirdParty/ | All imported packages (Mapbox, NWH, etc.) |
| Assets/StreamingAssets/ | Offline tile cache, OSM data files |
| Assets/Settings/ | URP assets, Input System assets |

1.4 — Core Architecture Decisions

Design Patterns to Use (implement from Day 1, never retrofit):

- ScriptableObject-based data — all bus specs, city configs, route data as ScriptableObjects, never hardcoded

- Service Locator or Dependency Injection — GameManager registers services, systems request them

- Event system — use C# events or Unity Events for all cross-system communication (no direct references)

- Scene architecture — one persistent Manager scene loaded additively, game scenes loaded on top

- Object Pooling — all buses, passengers, AI vehicles, rain particles must use pools from Day 1

⚠️  WARNING: If you skip object pooling and add it later, you will need to refactor every system that spawns GameObjects. This has derailed many solo projects. Pool from the start.

1.4A — Map Abstraction Layer

This is the single most important architectural decision in the entire project. Gameplay systems must never talk directly to Mapbox. If they do, a Mapbox SDK update, pricing change, or API break cascades through missions, passengers, and scoring simultaneously.

⚠️ WARNING: Do not let MissionManager or PassengerSystem call Mapbox APIs directly. Every system that reaches into the map provider becomes a liability. Getting this right in Phase 1 takes an afternoon. Fixing it in Phase 5 takes weeks.

Correct dependency chain:

- MapProvider interface: MapboxProvider, OSMProvider, MapLibreProvider — all implement the same interface

- MapSystem owns all tile loading, coordinate conversion, and road graph queries. It is the only layer that knows which provider is active

- Gameplay systems (RouteSystem, PassengerSystem, TrafficSystem) call MapSystem only. They have no knowledge of Mapbox

- BusRoute ScriptableObjects store your own GPS positions, not Mapbox objects

The result: MissionManager → RouteSystem → BusRoute ScriptableObjects → GPS positions. No map provider references anywhere in that chain.

✅ TIP: If you ever need to swap providers — Mapbox to MapLibre, for example — you change one class. Missions, passengers, scoring, and progression are completely untouched. Build this abstraction layer before writing any gameplay script.

1.5 — Initial Git Commit

Tasks:

- In project root: git init

- Add remote: git remote add origin git@github.com:yourname/realbus-simulator.git

- Stage all files: git add .

- Initial commit: git commit -m 'feat: initial Unity 6.3 URP project setup'

- Push: git push -u origin main

- Verify files appear on GitHub — confirm .meta files ARE present, .gitignore is correct

✅ TIP: Commit message convention to use throughout the project: feat: (new feature), fix: (bug fix), refactor: (restructure), docs: (documentation), test: (adding tests), chore: (maintenance). This makes your git log readable months later.

1.6 — Phase 1 Milestone

🎯 MILESTONE: Verify before Phase 2.

| # | Checkpoint | ✓ |
| --- | --- | --- |
| 1 | Project opens in Unity 6.3 LTS without errors | ☐ |
| 2 | URP configured with 3 quality levels | ☐ |
| 3 | Android build target configured (IL2CPP, ARM64, API 26+) | ☐ |
| 4 | Full folder structure created in Assets/ | ☐ |
| 5 | VS Code IntelliSense works on MonoBehaviour | ☐ |
| 6 | Initial Git commit pushed to GitHub | ☐ |
| 7 | A test APK builds and installs on S20 or A54 (even if just a blank screen) | ☐ |

PHASE 2: BUS PHYSICS CORE   [ Week 5–10 | ~60 hours ]

This is the hardest phase technically. The bus physics must feel right before you build anything else on top of them. A bus that feels wrong will never feel right no matter how good the maps or missions are. Take your time here.

2.1 — Test Environment

Tasks:

- Create a new scene: Scenes/PhysicsTestTrack.unity

- Create a flat 500m × 500m plane as the road surface

- Create a basic road material with friction value 0.7

- Add a Directional Light for visibility

- Create an empty GameObject named 'Bus_Root' — this is the parent for everything

- Add a Rigidbody to Bus_Root: Mass 12000, Drag 0.3, Angular Drag 0.5

- Set Rigidbody Interpolation to Interpolate (prevents jittery movement at low framerates)

- Set Collision Detection to Continuous Dynamic

2.2 — Wheel Collider Setup

⚠️  WARNING: WheelColliders are NOT child objects of the visual mesh. They are child GameObjects of the Bus_Root with separate visual wheel meshes that you update each frame. Getting this wrong breaks everything.

Tasks:

- Create 6 child GameObjects under Bus_Root: WheelCollider_FL, FR, ML, MR, RL, RR (front, middle, rear left/right)

- Add WheelCollider component to each

- Set wheel positions matching a standard 12m city bus wheelbase (~6.2m front-to-rear)

- Configure each WheelCollider: Radius 0.5, Mass 150, Suspension Distance 0.2

- Front axle spring: Spring 120000, Damper 6000, Target Position 0.5

- Rear axles spring: Spring 160000, Damper 8000, Target Position 0.5 (heavier load)

- Forward friction: Extremum Slip 0.4, Extremum Value 1.0, Asymptote Slip 0.8, Asymptote Value 0.6, Stiffness 1.2

- Sideways friction: Extremum Slip 0.25, Extremum Value 1.0, Asymptote Slip 0.5, Asymptote Value 0.75, Stiffness 1.0

- Create visual wheel meshes as separate child GameObjects

- Write WheelVisualSync.cs: in Update(), call WheelCollider.GetWorldPose() and apply position/rotation to visual mesh

2.3 — Engine & Transmission System

Tasks:

- Create EngineSystem.cs ScriptableObject: define torque curve as AnimationCurve (rpm vs Nm)

- Torque curve values: 500rpm=600Nm, 1200rpm=1200Nm (peak), 2000rpm=900Nm, 2500rpm=600Nm

- Create TransmissionSystem.cs: 6 gear ratios (3.5, 2.0, 1.35, 1.0, 0.82, 0.68) + reverse -4.5

- Calculate wheel torque: engineTorque × gearRatio × differentialRatio / wheelRadius

- Implement automatic gear shifting: shift up at 80% of peak RPM, shift down at 35%

- Apply torque to rear 4 WheelColliders only (rear-wheel-drive bus)

- Implement engine braking: when throttle=0, apply small negative torque scaled by RPM

- Add engine sound placeholder (simple AudioSource with pitch scaled by RPM)

2.4 — Steering System

Tasks:

- Steering applies only to front 2 WheelColliders

- Max steer angle: 42 degrees (city bus turning circle ~12m radius)

- Implement Ackermann steering geometry: inner wheel steers more than outer wheel

- Apply steering smoothing: use Mathf.Lerp with 0.1 coefficient to prevent snapping

- Implement speed-sensitive steering: at 80+ km/h reduce max angle to 8 degrees

- Test: bus should be able to make a U-turn in a standard two-lane road

2.5 — Braking & Retarder

Tasks:

- Service brake: apply brake torque to all 6 wheels, max 12000 Nm total

- Implement ABS: detect wheel slip (wheelRPM near 0 while moving), reduce brake torque 20%

- Retarder (engine brake on descents): when retarder active, apply resistance torque to drivetrain proportional to speed

- Parking brake: locks rear 4 wheels completely (for stops on hills)

- Implement brake fade: sustained heavy braking reduces effectiveness by up to 30% over 60 seconds, recovers when cool

2.6 — Bus-Specific Weight & Dynamics

Tasks:

- Set Rigidbody Centre of Mass to Y=1.6m (high CoM for roll behaviour)

- Implement dynamic CoM shift: as passengers load/unload, CoM shifts laterally and vertically

- Configure anti-roll bar simulation: apply corrective torques between paired wheel colliders

- Test body roll: at 40 km/h cornering, bus should visibly lean 3–5 degrees outward

- Test pitch: heavy braking should cause nose-down pitch of 1–2 degrees

2.7 — Aerodynamics

Tasks:

- Create AerodynamicsSystem.cs: calculate drag force = 0.5 × Cd × frontalArea × airDensity × velocity²

- Cd = 0.65, frontal area = 8.5m² (2.55m wide × 3.3m tall)

- Apply drag force via Rigidbody.AddForce() in FixedUpdate() opposing velocity direction

- Add crosswind simulation: apply lateral force at CoM proportional to crosswind speed (set from WeatherSystem later)

- Test: bus should reach ~88 km/h top speed naturally on flat road at full throttle

2.8 — Physics Validation Tests

Run each test and record results — do not proceed until all pass:

| Test | Expected Result | Pass Criteria | Result |
| --- | --- | --- | --- |
| 0–50 km/h time | ~18 seconds | Between 15–22s |  |
| 0–80 km/h time | ~55 seconds | Between 45–65s |  |
| Top speed (flat, full throttle) | ~88 km/h | Between 82–95 km/h |  |
| Emergency stop from 50 km/h | ~28m stopping distance | Between 22–35m |  |
| U-turn radius | ~12m | Completes in 24m wide space |  |
| Body roll at 40 km/h corner | Visible lean | 3–6 degrees outward |  |
| Hill start (10% grade) | No roll-back with parking brake | Pulls away without rollback |  |
| Laden (80 passengers) vs unladen | Noticeable performance difference | 0–50 time ~30% longer laden |  |

2.9 — Mobile Controls Prototype

Tasks:

- Install Unity Input System package via Package Manager

- Create InputActions asset: define Accelerate (button), Brake (button), Steer (axis), Retarder (button), Horn (button)

- Create MobileControlsUI.cs: on-screen buttons and steering wheel widget

- Implement three control schemes (see GDD Section 7) as selectable options

- Test on both S20 and A54 — verify touch responsiveness below 16ms latency

2.10 — Phase 2 Milestone

🎯 MILESTONE: Physics must feel RIGHT before you build anything else.

| # | Checkpoint | ✓ |
| --- | --- | --- |
| 1 | All 8 physics validation tests pass | ☐ |
| 2 | Bus controls responsively on both S20 and A54 | ☐ |
| 3 | Three control schemes implemented and selectable | ☐ |
| 4 | Physics runs at 60 FPS on S20, 30+ FPS on A54 | ☐ |
| 5 | No physics explosions or jitter at any tested speed | ☐ |
| 6 | Git commit: 'feat: bus physics core complete' | ☐ |

PHASE 3: REAL MAP INTEGRATION   [ Week 11–16 | ~60 hours ]

3.1 — Mapbox SDK Installation

Tasks:

- Download Mapbox Unity SDK from mapbox.com/unity — download the .unitypackage file

- In Unity: Assets → Import Package → Custom Package → select downloaded file

- Wait for import to complete (5–10 minutes)

- Go to Mapbox → Setup in Unity menu bar

- Enter your Mapbox Access Token (from the file you saved in Phase 0)

- Create a new scene: Scenes/MapTest.unity

- Add the Mapbox AbstractMap component to an empty GameObject

- Set map centre to a known location (e.g. Nairobi: -1.286389, 36.817223)

- Set zoom level 16, Map Style to Mapbox Streets

- Press Play — verify map tiles load and roads are visible

⚠️  WARNING: The Mapbox Unity SDK may have breaking changes between versions. If the SDK was built for Unity 2022 and you are using Unity 6.3, check the Mapbox GitHub for any Unity 6 compatibility patches before importing.

3.2 — Coordinate System Bridge

Unity uses a local 3D coordinate system in metres. Mapbox uses WGS84 latitude/longitude. You need a reliable bridge between them.

Tasks:

- Create CoordinateConverter.cs: wrap Mapbox's GeoToWorldPosition() and WorldToGeoPosition()

- Create a MapOrigin ScriptableObject: stores the GPS origin of the current map session

- Write unit tests for coordinate conversion (test round-trip conversion accuracy to within 0.1m)

- Create GpsTracker.cs: updates bus GPS position and feeds it back to minimap system

3.3 — Road Mesh & Physics Colliders

Mapbox generates visual tile meshes but they are not automatically physics-enabled. You need colliders on roads.

Tasks:

- Enable 'Mesh Colliders' on Mapbox road layer tiles

- Configure road layer to generate only road geometry (suppress buildings for now — add back in Phase 7)

- Apply road surface PhysicsMaterial: static friction 0.7, dynamic friction 0.6

- Create a road surface detector: raycast downward from each wheel, detect road type from layer tag, adjust WheelCollider friction stiffness accordingly

- Road types and friction: Asphalt=1.0×, Cobblestone=0.85×, Dirt=0.65×, Wet(rain)=0.7×

3.4 — Tile Streaming Manager

Tasks:

- Create TileStreamManager.cs: monitors bus GPS position, requests tiles within 2km radius

- Implement tile loading priority: closest tiles first, by distance from bus

- Implement tile unloading: destroy tiles further than 3km from bus

- Add loading indicator UI: show spinner when tiles are streaming

- Test streaming at 80 km/h on a motorway: tiles should load before bus reaches them

3.5 — Offline Cache System

Tasks:

- Enable Mapbox offline tile cache in SDK settings: set cache size to 500 MB

- Create OfflineCacheManager.cs: checks network connectivity on startup

- If online: stream tiles normally, cache automatically writes

- If offline: redirect tile requests to local cache

- Create CityPredownloader.cs: allows pre-downloading a city's tiles before driving

- UI: Settings → Offline Maps → select city → Download (shows progress bar and MB size)

- Test offline mode: put phone in Airplane mode, drive a pre-downloaded area

📌 NOTE: Mapbox caches tiles automatically in their SDK. Your OfflineCacheManager mainly needs to handle the UI and network detection logic, not the actual caching.

3.6 — OSM Road Network Query

Tasks:

- Study Overpass API query language at overpass-turbo.eu

- Create OverpassQueryBuilder.cs: generates queries for road network around a given GPS bounding box

- Sample query: [out:json]; way[highway~'motorway|primary|secondary|residential'](<bbox>); out geom;

- Create OverpassResponse.cs: deserialise JSON response into road node/way data

- Create RoadGraph.cs: build a navigable graph of road segments with speed limits and road types

- Test: query road network for a 2km × 2km area, verify graph has correct connectivity

3.7 — Bus Route Data from OSM

Tasks:

- Query OSM for bus routes: [out:json]; relation[route=bus](<bbox>); out geom;

- Create BusRouteParser.cs: extract route relation, ordered stop list, and route geometry

- Create BusStop.cs: stores stop name, GPS position, heading direction for alignment, stop ID

- Create BusRoute ScriptableObject: stores ordered list of BusStops, route number, destination name

- Visualise routes in Editor: create RouteDebugVisualiser.cs to draw route line in Scene view

- Test with at least 3 real routes from a city (Nairobi is well-mapped in OSM)

3.7A — Route Creation Tool

Manually positioning bus stops and drawing route paths city by city is not a viable workflow for a solo developer who wants to support multiple cities post-launch. Build a Route Creation Tool as a Unity Editor extension during this phase. It converts raw OSM data into validated BusRoute ScriptableObjects with minimal manual intervention. A city that would take two full days to build by hand takes under two hours with this tool.

✅ TIP: This tool pays for itself on the second city you add. Build it once in Phase 3 and every post-launch city becomes a 30–90 minute task instead of a two-day project.

Tasks:

- Create OSMRouteImporter.cs Editor tool: queries the Overpass API, downloads road and bus stop data for a user-defined bounding box, parses the response JSON into RoadGraph nodes and BusStop objects

- Stop snap algorithm: for each imported stop, find the nearest road segment in the RoadGraph and project the stop position onto it — OSM stop coordinates are frequently offset from the road centre

- Corridor clustering: group stops within 200—400m spatial proximity into route corridor candidates — each cluster becomes one draft route

- Route path generation: connect ordered stops within each cluster using A* pathfinding on the RoadGraph, guaranteeing the bus path follows real road geometry between every stop

- Route filter pass: discard candidates below 6 stops, above 40 stops, below 3 km, or above 25 km. The filtered result is 10–20 usable routes per city

- Create RouteEditorWindow.cs: a Unity Editor window showing the map with routes drawn as coloured lines and stops as drag-and-drop markers. Operations: move stop, delete stop, add stop, reorder, split route, merge routes

- Return route auto-generation: for every saved route, create a return variant by reversing stop order and re-running pathfinding

- Route difficulty classifier: urban dense route = difficulty 4, highway = difficulty 2, suburban = difficulty 3. This output feeds directly into the progression unlock system

- Save final output as BusRoute ScriptableObject in Assets/_Game/Routes/ containing routeName, stops[], pathPoints[], distance, estimatedTime, difficulty

⚠️ WARNING: Do not attempt to generate routes for every city up front. Build city data on demand via city packs. Storage, API call costs, and gameplay balance all depend on keeping city data scoped to what the player has actively downloaded.

3.8 — City Configuration System

Tasks:

- Create CityConfig ScriptableObject: cityName, gpsCenter, availableRoutes[], defaultZoom, predownloadSizeMB

- Create initial city configs for: City 1 (tutorial city), with placeholder for 4 more

- Create CitySelector.cs: loads city, moves map origin, queries OSM for that city's routes

3.9 — Phase 3 Milestone

🎯 MILESTONE: Real world map must be driveable before gameplay systems begin.

| # | Checkpoint | ✓ |
| --- | --- | --- |
| 1 | Map tiles stream correctly around moving bus | ☐ |
| 2 | Bus drives on road surface with correct physics colliders | ☐ |
| 3 | Offline mode works on pre-downloaded area (tested with Airplane mode) | ☐ |
| 4 | At least 3 real bus routes loaded from OSM with correct stop positions | ☐ |
| 5 | Bus stops rendered at correct GPS positions on map | ☐ |
| 6 | No tile loading stutters at 80 km/h | ☐ |
| 7 | Git commit: 'feat: real map integration complete' | ☐ |

PHASE 4: CORE GAMEPLAY LOOP   [ Week 17–24 | ~80 hours ]

4.1 — Free Drive Mode

Tasks:

- Create FreeDriveSession.cs: starts a session, tracks distance driven, enables open-world driving

- Create FreeDriveUI.cs: shows speedometer, fuel gauge, current GPS, distance odometer

- No objectives, no timer, no passengers

- Fuel still depletes — adds to realism even in free drive

- Add photo mode: pause game, free camera, screenshot button

4.2 — Route Mission Framework

Tasks:

- Create MissionManager.cs: singleton that manages active mission state

- Create MissionState enum: NotStarted, Briefing, InProgress, AtStop, Completed, Failed

- Create MissionData ScriptableObject: route reference, scheduled departure time, passenger count targets, time bonuses

- Create MissionBriefing UI: shows route map, scheduled stops, expected duration, difficulty rating

- Implement mission start sequence: departure countdown from depot

4.3 — Stop Approach & Docking System

Tasks:

- Create StopTrigger.cs: trigger zone 50m before each stop — activates approach guidance

- Create DockingZone.cs: at-stop zone — bus must be within 0.5m of kerb, within 3m of stop sign

- Implement door logic: doors only open when correctly docked

- Create approach guidance UI: arrow and distance display as bus approaches stop

- Kneeling suspension: when docked, lower bus body 80mm to kerb level (animating the air suspension target position)

- Bell system: ring bell sound when door open button pressed, and when passenger requests next stop

4.4 — Schedule & Punctuality System

Tasks:

- Create ScheduleManager.cs: tracks expected arrival time vs actual time at each stop

- Create in-game clock: runs at 1× real time (no time acceleration in base mode)

- Status display: On Time (±60s), Early (>60s early), Late (>60s late), Severely Late (>3min)

- Implement early arrival penalty: if too early at a stop, must wait until scheduled time

- Implement late arrival scoring reduction: -2% score per 30 seconds late

- Create ScheduleDebugOverlay for development: shows all stops with expected vs actual ETA

4.5 — Scoring System

Tasks:

- Create ScoreTracker.cs: accumulates score in real-time during mission

- Implement Punctuality Score (30%): calculated at each stop

- Implement Passenger Satisfaction Score (30%): degrades on hard braking (>0.4g), sharp corners (>0.3g lateral), sudden acceleration

- Implement Safety Score (25%): collision detection, traffic signal compliance, speed limit violations

- Implement Fuel Efficiency Score (15%): compare actual vs target L/100km

- Mission completion screen: breakdown of all 4 score categories, XP earned, time taken

- Create ScoreDisplay.cs: live score visible during mission as collapsible HUD panel

4.6 — Traffic Signal Compliance

Tasks:

- Query OSM for traffic signal nodes: node[highway=traffic_signals](<bbox>)

- Create TrafficLight.cs: cycles through Red (45s) → Green (35s) → Amber (5s)

- Phase offset each intersection to prevent all signals turning green simultaneously

- Create SignalViolationDetector.cs: trigger zone at stop line, detect if bus crosses on red

- Red light violation: -500 points, logged in mission report

4.7 — Mission Results & XP

Tasks:

- Create MissionResult.cs: final score %, star rating (1–5), XP earned, coins earned

- XP formula: baseXP × (score/100) × difficultyMultiplier

- Base XP per mission: 200 (1-star route) to 1000 (5-star route)

- Create MissionResultScreen UI: animated score reveal, star pop-in, XP bar fill

- Persist results to PlayerPrefs (temporary) — replaced with PlayFab in Phase 6

4.8 — Phase 4 Milestone

🎯 MILESTONE: Complete a real mission end-to-end before building realism systems.

| # | Checkpoint | ✓ |
| --- | --- | --- |
| 1 | Free Drive mode playable on real map | ☐ |
| 2 | Route mission starts, plays, and ends with result screen | ☐ |
| 3 | All 4 scoring categories calculating correctly | ☐ |
| 4 | Stop docking works within tolerance | ☐ |
| 5 | Traffic signals cycle and violations are detected | ☐ |
| 6 | Mission completable on S20 at 60 FPS | ☐ |
| 7 | Git commit: 'feat: core gameplay loop complete' | ☐ |

PHASE 5: REALISM SYSTEMS   [ Week 25–34 | ~100 hours ]

5.1 — Passenger Agent System

Tasks:

- Create PassengerAgent.cs: stores origin stop, destination stop, patience timer, satisfaction value

- Create PassengerSpawner.cs: spawns passengers at stops based on time-of-day density curves

- Rush hour curve: peak at 7:30am and 5:30pm, 5× baseline density

- Boarding animation: simple lerp from platform position to seat/standing position

- Standing passengers: apply sway force inverse to bus acceleration/deceleration

- Alighting: destination stop reached → passenger moves to door → exits

- Wheelchair passenger: random 5% chance — requires kneeling suspension and 10s extra dwell time

- Implement passenger capacity enforcement: doors refuse to open if at 80/80 capacity

- Create PassengerCountUI: shows current/max passenger count and satisfaction emoji

5.2 — AI Traffic System

Tasks:

- Create VehiclePool.cs: pool of 50 AI vehicles (cars, trucks, motorcycles) per scene

- Create AIVehicleController.cs: follows road graph, obeys speed limits and traffic signals

- Implement lane keeping: AI stays in correct lane, maintains safe following distance

- Implement overtaking logic: AI overtakes stopped buses correctly

- Create PedestrianSpawner.cs: pedestrians at zebra crossings, interact with traffic signals

- Traffic density system: query time-of-day, set spawn rate accordingly

- Emergency vehicle: create AmbulanceBehaviour.cs — plays siren, all traffic pulls over

- AI buses: spawn other buses on their routes — creates realistic traffic with a schedule

⚠️  WARNING: AI traffic is one of the most performance-intensive systems. Profile on A54 specifically. Use Unity DOTS/ECS if standard MonoBehaviour AI causes frame drops below 30 FPS.

5.2A — AI Traffic Architecture

The AIVehicleController.cs system in 5.2 uses MonoBehaviour. At 20 vehicles this performs acceptably. At 50 vehicles on a Samsung A54, each vehicle carrying its own physics simulation, pathfinding, sensor raycasts, and traffic rule evaluation will produce frame drops to 20 FPS or below, stuttering traffic visible to the player, and sustained device overheating. Traffic is a core visible system. Its failure is immediately apparent.

⚠️ WARNING: Profile vehicle count on A54 before setting a target number. Do not assume the vehicle cap you can run on your dev machine translates to the A54. The gap is significant.

Tasks:

- Implement a distance-based AI tier split in VehiclePool.cs: vehicles within 200m of the bus run full AIVehicleController (physics, pathfinding, signal compliance); vehicles at 200—400m switch to SplineVehicle.cs

- Create SplineVehicle.cs: follows a path array derived from the RoadGraph, adjusts speed when approaching a red light, maintains a minimum headway gap from the vehicle ahead. No physics simulation, no raycasting, minimal CPU cost

- Tier transition: when a spline vehicle crosses inside the 200m threshold, swap it to a full AIVehicleController instance with matching position and velocity. The swap must be invisible to the player

- Hard cap full-AI vehicles at 15—20 simultaneously regardless of total pool size — this is the non-negotiable performance budget for A54

- Create an AI traffic stress test scene: spawn vehicles incrementally on A54, record the FPS at each count. That cliff point is the maximum vehicle budget for the entire game

Players cannot distinguish spline movement from physics-based movement at distances beyond 150m. The perceptual quality difference is zero; the performance benefit is substantial.

📌 NOTE: Unity DOTS/ECS can simulate hundreds of vehicles efficiently and is the correct long-term solution if you ever need higher traffic density. It is not appropriate for the initial solo build. Treat it as a post-launch upgrade path only if the hybrid architecture proves insufficient at your target vehicle count.

5.3 — Weather System

Tasks:

- Create WeatherSystem.cs: manages active weather state and transitions

- Weather states: Clear, Overcast, LightRain, HeavyRain, Fog, Night (composable)

- Create RainController.cs: particle system for rain, wet road shader activation, windscreen wiper animation

- Wet road shader: blend normal road albedo with wet specular material based on rain intensity

- Create FogController.cs: Unity volumetric fog, adjust density based on fog intensity

- Night mode: activate street light GameObjects, activate bus headlights, increase shadow contrast

- Weather affects physics: modify WheelCollider sidewaysFriction.stiffness based on weather

- Weather transition: lerp between states over 3–5 minutes for realism

- WeatherUI: small icon in HUD corner showing current weather

5.4 — Day/Night Cycle

Tasks:

- Create TimeOfDaySystem.cs: in-game clock, controls sun angle via Directional Light rotation

- Sky colour gradient: dawn (orange), day (blue), dusk (red-orange), night (dark blue)

- Ambient light intensity curve matched to sun angle

- Street lights auto-activate at sunset, deactivate at sunrise

- Bus interior lights auto-activate at night

- Passenger density linked to time of day (see 5.1)

5.5 — Fuel & Maintenance System

Tasks:

- Create FuelSystem.cs: tank capacity 300L, consumption calculated per FixedUpdate

- Fuel consumption formula: baseLPer100km × loadFactor × RPMefficiencyFactor × roadGradientFactor

- City driving base: 35 L/100km, motorway base: 28 L/100km

- Full passenger load increases consumption by 18%

- Fuel warning at 20% tank, critical warning at 5%

- Refuel at depot: automatic refuel when mission ends at depot, deducted from earnings

- Create MaintenanceSystem.cs: tracks brake wear, tyre wear, engine hours

- Brake wear: heavy service brake use degrades faster than retarder use

- Tyre wear: tracked per axle, affects grip stiffness after 50% wear

- Maintenance UI: visible in depot/garage screen, shows condition bars for each system

- Maintenance cost deducted from mission earnings automatically

5.6 — Performance Optimisation Pass #1

⚠️  WARNING: After adding all realism systems, performance on A54 will likely have degraded. This optimisation pass must happen before Phase 6.

Tasks:

- Profile on A54 using Unity Profiler over USB: identify top 3 CPU bottlenecks

- Profile GPU: use Mali Graphics Debugger if available, identify overdraw hotspots

- Implement LOD (Level of Detail) on bus model: full detail <100m, reduced >100m, billboard >300m

- Implement tile mesh LOD: reduce road mesh detail beyond 500m

- Cull AI vehicles beyond 400m from bus

- Reduce rain particle count on Low quality setting

- Target: A54 maintains 30+ FPS with 20 AI vehicles, light rain, full passengers

5.6A — Tile Level of Detail

The TileStreamManager from Phase 3 loads tiles within a 2–3 km radius. If every tile in that radius carries full mesh geometry, full-resolution textures, and active colliders simultaneously, peak RAM usage reaches 1–2 GB. Mid-range phones will terminate the process. This is the most common cause of out-of-memory crashes in mobile map games during extended sessions.

⚠️ WARNING: Tile streaming radius and tile detail level are independent variables. A 2 km streaming radius with full-detail tiles at every distance is far more expensive than the streaming system alone implies. LOD tiers are not optional on mobile.

Tasks:

- Extend TileStreamManager with a three-tier LOD system keyed on distance from the bus position, recalculated each time a tile crosses a threshold

- Tier 1 (0–200m from bus): full geometry, full-resolution textures, active mesh colliders. This is the zone the player sees in close detail and drives on

- Tier 2 (200–500m from bus): simplified mesh at 40% of Tier 1 polygon count, compressed textures, colliders inactive

- Tier 3 (500–2000m from bus): flat texture quad, no mesh geometry, no colliders, background fill only

- All LOD swaps trigger asynchronously on a background thread. Never swap tile detail level synchronously mid-frame

This system reduces peak concurrent memory by 60–70% compared to uniform full-detail streaming. At bus speeds, the visual difference at 200m is imperceptible.

✅ TIP: Implement tile LOD during this optimisation pass. It is one of the highest-return tasks in the project relative to the time it takes to build.

5.7 — Phase 5 Milestone

🎯 MILESTONE: All realism systems active simultaneously without frame drops.

| # | Checkpoint | ✓ |
| --- | --- | --- |
| 1 | Passengers spawn, board, ride, and alight correctly | ☐ |
| 2 | 20+ AI vehicles active without FPS drop below 30 on A54 | ☐ |
| 3 | All weather states render correctly and affect physics | ☐ |
| 4 | Day/night cycle completes without visual artefacts | ☐ |
| 5 | Fuel depletes at correct rate, maintenance costs apply | ☐ |
| 6 | Full realism mission playable: passengers + traffic + weather + day/night | ☐ |
| 7 | Git commit: 'feat: all realism systems integrated' | ☐ |

5.8 — Additional Simulation Systems

The systems below are not on the critical path to launch. Each meaningfully increases simulation depth or player retention and can be added during Phase 5, Phase 6, or as post-launch updates depending on timeline. They are ordered by implementation effort.

5.8.1 — Driver Shift System

Simulation depth in bus games comes from the job, not just the route. Add a shift structure: players start at the depot, complete a pre-drive inspection, sign in to the rota, run multiple routes within a timed shift, and return the bus at the end. This changes the rhythm from individual runs to a working day.

- Pre-drive inspection: check tyre condition, fuel level, door function, exterior lights. Defects found here feed into the maintenance system

- Shift duration: 30–90 minutes of in-game time covering 2–4 routes

- Scheduled break stops: driver breaks are a legal requirement. Missing them applies a scoring deduction

- End of shift: return bus to correct bay, review full shift summary covering punctuality, incidents, fuel consumption, and passenger satisfaction

5.8.2 — Interactive Dashboard

Make the cockpit interactive, not just visual. Architecture: a central BusController with DoorSystem, LightSystem, WiperSystem, and BrakeSystem components. HUD buttons and physical dashboard switches call the same underlying functions — the dashboard is a second input layer, not a duplicate system.

- Primary HUD controls (fast access during driving): accelerate, brake, steer, horn, indicators, door open/close, hazard lights

- Secondary dashboard controls (optional, cockpit view): interior lights, kneeling suspension, parking brake, retarder level, ticket machine, air conditioning

- Every interaction must trigger all three feedback channels: switch animation, indicator light state change, audio

✅ TIP: On mobile, briefly highlight a tapped dashboard control and nudge the camera toward it. This makes small touch targets reliably usable and gives satisfying feedback for players in cockpit view.

5.8.3 — Mirror System

Mirrors are not cosmetic in a bus simulator. Drivers use them constantly for stop approach alignment, door-side clearance, and lane changes. Implement using RenderTexture cameras mounted at each mirror position. Budget one camera render call per active mirror per frame.

- Left door mirror, right door mirror, interior rear-view mirror

- Optional nearside blind-spot mirror for low-speed manoeuvring near kerbs

- Quality-scaled resolution: 256px on Low, 512px on Medium and High. Disable mirrors entirely on the lowest device tier if needed

5.8.4 — Extended Traffic Violations

The red-light detection from section 4.6 is the foundation. Extend it to cover the full range of driver infractions. Every violation is logged in the mission debrief and affects the score breakdown, XP earned, and the driver reputation rating introduced in Phase 6.

- Speeding: speed exceeds the road limit stored in RoadGraph. Penalty scales with the margin above limit

- Illegal turns: bus turns at a node where OSM data records a turn restriction

- Yellow light: bus front axle crosses the stop line during the amber phase

- Pedestrian conflict: bus within collision threshold of a pedestrian inside a designated crossing zone

- Junction blocking: bus body straddles an intersection while stationary

- Off-route deviation: bus centre point departs more than 50m from the active route path for more than 10 seconds

5.8.5 — Driveable Depot

Replace the static garage menu screen with a driveable depot environment. Players physically manoeuvre the bus into the parking bay, pull up to the fuel pump, and drive through the wash. Scope: parking bays, fuel station, bus wash, maintenance bay. This is the highest-effort item in this section and the most transformative for simulator feel. Schedule for Phase 7 or post-launch v1.1.

5.8.6 — Passenger Behaviour Depth

The passenger agent from 5.1 handles boarding, riding, and alighting. These additions layer personality and consequence on top of that foundation.

- Passenger archetypes: commuters (impatient, visible watch-checking animation), tourists (slow to board, ask about stop names), students (board in groups, take longer to clear the door), elderly (require kneeling suspension deployed before boarding, 10 seconds extra dwell time minimum)

- Reactive behaviour: passengers complain audibly above 0.5g braking, stand up and shuffle toward the door before their stop, press the stop request button

- Stop request bell: a passenger press illuminates the cab stop indicator and triggers the bell sound. The indicator must be acknowledged before the stop or it counts as a missed service

- Satisfaction pipeline: the passenger satisfaction value from 5.1 feeds directly into the post-mission star rating if it drops below 60%

5.8.7 — Dynamic Events

Random in-world events during missions prevent routes from becoming fully predictable after multiple completions. Events are weighted by city, time of day, and active weather state to remain contextually plausible.

- Traffic accident: road ahead blocked, minimap shows detour

- Planned road closure: signed diversion via alternate route

- Police checkpoint: mandatory slow zone, scoring observes compliance

- Construction zone: temporary speed limit reduction, single-lane passing

- Signal failure at intersection: treat intersection as give-way, scoring rules adjusted for the duration

- Sudden weather transition: weather state changes mid-route, physics modification applied immediately

5.8.8 — Achievements

A focused achievement set tied to natural skill and progression milestones. Avoid time-based padding. Good candidates: Perfect Route (100% combined score on any single route), 1,000 Passengers Transported, 50 Missions Completed Without an Incident, All Cities Unlocked, Grand Tour Completed. Achievements should require skill or meaningful persistence.

5.8.9 — Analytics

Integrate Firebase Crashlytics and Unity Analytics before the Phase 8 beta begins. Track: mission quit points, average FPS by device model, completion rate by route, most common violation type, least-used buses. Without this data, post-launch updates are guesswork. This is especially important for a solo developer who cannot run broad in-person playtests.

⚠️ WARNING: Do not enter beta without crash reporting active. Device-specific crashes on hardware you do not own will surface in store reviews before you have any data to diagnose them. The analytics setup takes one session to integrate. Do not skip it.

PHASE 6: PROGRESSION & META SYSTEMS   [ Week 35–42 | ~80 hours ]

6.1 — XP & Rank System

Tasks:

- Create XPSystem.cs: tracks total XP, current rank (1–10), XP to next rank

- Implement all 10 rank thresholds from GDD Section 6.1

- Create RankUpSequence.cs: animated rank-up screen with new rank title and unlock reveal

- Create XPBar UI component: visible on main menu and mission result screen

- Persist XP to PlayFab (cloud) and PlayerPrefs (local backup)

6.2 — City & Route Unlock System

Tasks:

- Create UnlockManager.cs: checks rank against unlock requirements, gates content

- Configure all 5 cities as locked by default, unlock at ranks 1/3/5/6/8

- Create CitySelectScreen UI: world map showing locked/unlocked cities

- Lock visual: greyed-out city with padlock icon and 'Unlock at Rank X' tooltip

- Route difficulty rating (1–5 stars) displayed on route selection screen

- 'Grand Tour' route: auto-generated concatenation of all routes in a city, unlocks on 100% completion

6.3 — Bus Fleet System

Tasks:

- Create BusSpec ScriptableObject: all physics parameters, model reference, capacity, fuel tank

- Configure at least 5 bus types: Standard Single-Decker, Articulated 18m, Double-Decker, Electric, Minibus

- Create GarageScreen UI: shows owned and locked buses, their specs side-by-side

- Unlock buses at specific ranks (see GDD Section 6.1)

- Electric bus: FuelSystem disabled, replaced by BatterySystem.cs — same logic, different values

6.4 — Livery Editor

Tasks:

- Create LiveryEditor.cs: runtime texture painting system using RenderTexture

- Livery zones: Roof, Front, Side Panel A, Side Panel B, Rear, Wheel Arches

- Controls: colour picker (HSV), paint bucket (fill zone), opacity slider

- Preset liveries: 8 classic operator-inspired colour schemes unlockable via rank

- Livery code: serialise livery data to a 12-character alphanumeric code, shareable

- Livery code input: text field that applies another player's livery code

6.5 — Performance Upgrades

Tasks:

- Create UpgradeManager.cs: tracks purchased upgrades per bus

- Implement all 5 upgrades from GDD Section 6.3 as modifier ScriptableObjects

- Each upgrade is a multiplier applied to the relevant physics or fuel parameter

- Upgrade purchase UI in Garage screen

- Upgrades persist in cloud save

6.6 — Save System

Tasks:

- Create SaveManager.cs: serialises all player data to JSON

- SaveData structure: playerXP, rank, unlockedCities[], unlockedBuses[], activeUpgrades{}, liveries[], missionHistory[]

- Local save: PlayerPrefs for quick save on app pause/close

- Cloud save: PlayFab's CloudScript for persistent cross-device save

- Implement save conflict resolution: cloud save wins if newer, prompt player if ambiguous

- Auto-save: trigger on mission complete, rank up, upgrade purchase, app background

6.7 — Phase 6 Milestone

🎯 MILESTONE: Complete progression loop functional end-to-end.

| # | Checkpoint | ✓ |
| --- | --- | --- |
| 1 | XP earns from missions and triggers rank-up at correct thresholds | ☐ |
| 2 | Cities and buses unlock at correct ranks | ☐ |
| 3 | Livery editor saves and restores liveries correctly | ☐ |
| 4 | Upgrades measurably affect physics parameters | ☐ |
| 5 | Save data persists across app restarts (local and cloud) | ☐ |
| 6 | Git commit: 'feat: full progression and meta systems' | ☐ |

PHASE 7: POLISH, AUDIO & UX   [ Week 43–50 | ~80 hours ]

7.1 — Full HUD Implementation

Tasks:

- Create HUDManager.cs: manages all HUD elements, toggles visibility based on game state

- Analogue speedometer: needle rotates, 0–120 km/h scale

- Gear indicator: current gear displayed prominently

- Route progress bar: horizontal bar with stop markers, bus icon moves along

- Next stop display: stop name and ETA

- Schedule status: colour-coded pill (green=on time, amber=warning, red=late)

- Passenger counter: icon + X/80 count

- Fuel gauge: analogue dial

- Engine temperature gauge: dial with red zone warning

- Minimap: circular, north-up, shows route, stops, bus position, toggleable

- All HUD elements respect Safe Area on notched phones

7.2 — Menu System

Tasks:

- Main Menu: Play, Garage, Settings, Credits

- City Select screen: world map with animated city pins

- Route Select screen: list of routes with star rating, best score, last played

- Garage screen: bus roster, upgrade shop, livery editor access

- Settings screen: control scheme, graphics quality, audio levels, language

- Pause menu: accessible during missions, shows current score breakdown

- Loading screen: shows city name and a driving tip while map loads

7.3 — Audio Implementation

Tasks:

- Install FMOD Studio plugin for Unity (free for indie developers)

- Create FMOD project: define all audio events

- Engine audio: multi-layer loop with RPM-driven pitch and load-driven mix (diesel thrum, turbo whine, exhaust crackle on deceleration)

- Tyre sounds: rolling hiss (speed-driven), squeal (slip-driven), wet spray (rain mode)

- Brakes: squeal on heavy application, air brake hiss on release

- Interior ambience: passenger chatter (volume scales with passenger count), air conditioning hum

- Exterior ambience: city noise, traffic, birds, wind

- UI sounds: button clicks, mission start/end fanfare, rank-up jingle

- Horn: air horn with correct bus reverb

- Spatial audio: sounds positioned correctly in 3D world

7.4 — Visual Polish

Tasks:

- Bus exterior: create or acquire detailed bus 3D model with proper UV mapping

- Interior: basic but recognisable interior — seats, poles, driver cabin

- Bus glass: semi-transparent with environment reflections

- Damage system (cosmetic only): bus body texture shows scuffs after collisions

- Particle effects: exhaust smoke (heavier under load), rain splash on windows, dust on dirt roads

- Post-processing URP volume: subtle bloom, colour grading (slightly warm for city, cooler for highway)

- Lens flare on oncoming headlights at night

- Motion blur: subtle, hardware-accelerated, disable on Low quality

7.5 — Accessibility

Tasks:

- Font size: all UI text minimum 28sp on mobile

- Colour blind mode: replace colour-only indicators with icons + colour

- High contrast mode: increase UI element contrast ratio

- Haptic feedback: short vibration on docking, collision, mission complete

- Subtitle system for any voice content (none planned but build the scaffolding)

7.6 — Performance Optimisation Pass #2

Tasks:

- Profile full game session (45 minute mission) on A54

- Memory profiling: check for memory leaks in tile loading/unloading cycle

- Thermal testing: play for 30 minutes on A54 — check for thermal throttling (use CPU-Z app)

- Battery drain test: measure % battery used per 30 minutes of play — target <15%

- Fix any remaining frame drops, stutters, or hitches

7.7 — Phase 7 Milestone

🎯 MILESTONE: Game must be enjoyable to play before entering QA.

| # | Checkpoint | ✓ |
| --- | --- | --- |
| 1 | Full HUD implemented with all elements | ☐ |
| 2 | Complete menu flow from launch to mission and back | ☐ |
| 3 | FMOD engine audio sounds authentic at all RPM and load states | ☐ |
| 4 | 30-minute play session on A54 without crash or thermal shutdown | ☐ |
| 5 | At least 3 playtesters complete a mission without instruction | ☐ |
| 6 | Git tag: v0.9-beta | ☐ |

PHASE 8: QA, BETA & LAUNCH   [ Week 51–72 | ~5 months ]

8.1 — Internal QA (Weeks 51–54)

Test Matrix — test every combination:

| Test Category | Cases | Pass Criteria |
| --- | --- | --- |
| Device compatibility | S20 (high), A54 (mid), 1 low-end device if available | Runs at 30+ FPS, no crashes |
| Android OS versions | Android 10, 12, 14 | No OS-specific crashes |
| Network conditions | 4G, WiFi, Offline, Flaky connection | Graceful fallback in all cases |
| Session length | 5 min, 30 min, 60 min | No memory leaks, no thermal shutdown on A54 |
| Mission completion | All routes in City 1, all weather, all times of day | 100% completion rate |
| Progression | Level 1 to Level 5 full playthrough | All unlocks trigger correctly |
| Edge cases | 0% battery, incoming call during play, orientation change | No data loss, graceful resume |
| Save/load | Force-quit mid-mission, restore, repeat 10× | Progress always preserved |

8.2 — Bug Triage Process

Severity classification:

- P0 — Crash or data loss: fix within 24 hours, rebuild immediately

- P1 — Major gameplay break (mission uncompletable): fix within 72 hours

- P2 — Noticeable bug, workaround exists: fix before launch

- P3 — Minor cosmetic or edge case: fix if time permits

8.3 — Beta Testing (Weeks 55–62)

Tasks:

- Register for Google Play Early Access program

- Set up Apple TestFlight for iOS beta (requires Apple Developer account — $99/year)

- Recruit 20–50 beta testers via Reddit (r/AndroidGaming, r/iosgaming), Discord, friends

- Provide beta testers with a structured feedback form covering: controls feel, frame rate, map accuracy, fun factor, bugs

- Run 2-week beta sprints: collect feedback → fix P0/P1 → new build → repeat

- Monitor crash reports via Unity Gaming Services or Firebase Crashlytics

- Track retention: what % of beta testers play more than 3 sessions?

8.4 — Store Preparation (Weeks 63–67)

Google Play Store:

- Create developer account ($25 one-time fee)

- Create store listing: title, short description (80 chars), full description (4000 chars)

- Create screenshots: 8 screenshots per device form factor (phone + tablet)

- Create feature graphic: 1024 × 500px

- Create privacy policy (required for apps with internet access) — use a free generator

- Set content rating: complete IARC questionnaire (likely PEGI 3 / Everyone)

- Configure pricing: Free

- Create ProGuard/R8 config to protect compiled code

Apple App Store:

- Enrol in Apple Developer Program ($99/year)

- Create App Store Connect listing

- Screenshots: 6.7-inch, 6.5-inch, 5.5-inch required

- App Store review notes: explain map data source and internet usage

8.4A — APK Size Management

The 100 MB initial download limit is a hard constraint for Google Play distribution and a significant signal to users about install friction. Every megabyte over 100 MB costs a percentage of potential installs on mid-range devices where storage is scarce. The solution is straightforward: ship a small core game and download city content on demand. Every successful mobile open-world game uses this model.

Core APK target: 70–90 MB

The APK contains only reusable systems and the minimum content needed for the first session. No city-specific data belongs here except the tutorial.

- All game engine systems: bus physics, traffic simulation, passenger system, UI

- One starter bus model with base livery texture

- Tutorial city: limited tile coverage, 2–3 routes, sufficient to complete the onboarding sequence

- All shared audio, shaders, and UI assets

Tasks:

- Create CityManager.cs with LoadCityBundle(), UnloadCityBundle(), LoadRoutes(), LoadStops() — cities are never referenced directly in the build, only loaded at runtime

- Build per-city Asset Bundles: each bundle contains the road graph data, BusRoute ScriptableObjects, stop location data, and minimap assets for one city. No game logic. Typical bundle size: 20—80 MB

- City download UI: city name, download size in MB, download progress bar. Trigger on first city selection, not at install

- Enable Google Play Asset Delivery for city bundles. Delivery routes through Google infrastructure and does not count against the 100 MB APK size limit

- Set tile cache ceiling at 500 MB in OfflineCacheManager.cs. Purge least-recently-used tiles when exceeded. The full city map is never stored on device at once

- Enable ASTC texture compression across all textures for Android. A 1024×1024 texture drops from approximately 4 MB to 1 MB

- Single bus mesh with runtime livery swapping via RenderTexture. Never duplicate the mesh per colour variant

- Generate city buildings procedurally from OSM building footprint and height attributes at runtime. Do not store building geometry in bundles

Route data is negligible in size: a BusRoute ScriptableObject with 20 stops and its path points is 5–20 KB. One hundred routes total less than 2 MB. The size risk in any mobile game is always textures and geometry, never route data.

✅ TIP: Smaller city bundles improve runtime performance as well as install size. A 35 MB city pack uses less memory, loads faster, and puts less pressure on the battery than a 150 MB equivalent. The size discipline benefits both the install funnel and in-session performance on A54.

8.5 — Performance & Size Optimisation (Weeks 63–67)

Tasks:

- Enable Unity's texture compression: ASTC for Android (best quality/size balance)

- Enable Asset Bundle variant system for language/resolution bundles

- Strip unused Unity engine code: Player Settings → Managed Stripping Level → High

- Enable IL2CPP link.xml to preserve only needed assemblies

- Target APK size below 100 MB initial download (use Asset Delivery for additional content)

- Enable Google Play Asset Delivery for city map packs (download on demand)

8.6 — Soft Launch (Weeks 68–70)

Tasks:

- Release to 2–3 small markets first (e.g. Kenya, Ghana, Uganda — you have local knowledge)

- Monitor: Day 1 retention, Day 7 retention, crash rate, review sentiment

- Fix any critical issues before global launch

- Target: Day 1 retention >40%, crash rate <1%, average review >3.8 stars

8.7 — Global Launch (Weeks 71–72)

Tasks:

- Enable full worldwide availability on Google Play

- Submit to App Store (Apple review typically takes 2–5 days)

- Prepare press kit: game description, 10 screenshots, trailer video link, contact email

- Post to: r/AndroidGaming, r/iosgaming, r/Unity3D (devlog), Twitter/X, LinkedIn

- Submit to mobile game review sites: Pocket Gamer, TouchArcade, Droid Gamers

- Monitor reviews daily for first 2 weeks and respond to all reviews

8.8 — Post-Launch (Ongoing from Week 73)

Recurring Tasks:

- Weekly: review crash reports, fix P0/P1 bugs, respond to reviews

- Monthly: new city release (OSM data makes this faster than building from scratch)

- Quarterly: new bus type, major feature update

- Ongoing: OSM data updates (roads change — re-query and update route data)

8.9 — Launch Milestone

🎯 FINAL MILESTONE: Launch Readiness.

| # | Checkpoint | ✓ |
| --- | --- | --- |
| 1 | Crash rate below 1% across all tested devices | ☐ |
| 2 | APK size below 100 MB | ☐ |
| 3 | All P0 and P1 bugs resolved | ☐ |
| 4 | Store listings complete on both platforms | ☐ |
| 5 | Privacy policy live and linked in store | ☐ |
| 6 | Soft launch Day 1 retention above 40% | ☐ |
| 7 | Git tag: v1.0-release | ☐ |
| 8 | App live on Google Play and Apple App Store | ☐ |

Recurring Tasks Throughout All Phases

🔁 These tasks happen on a fixed schedule regardless of which phase you are in.

| Frequency | Task | Time Required |
| --- | --- | --- |
| Every coding session | Git commit with descriptive message before stopping work | 2 minutes |
| Every coding session | Test on at least one physical device (S20 or A54) | 5–10 minutes |
| Daily | Back up project to GitHub (git push) | 1 minute |
| Weekly | Full build test: clean build APK and install on A54 | 20–30 minutes |
| Weekly | Review GDD against what is built — update GDD if design changes | 15 minutes |
| Weekly | Check Mapbox dashboard: API usage vs free tier limit | 2 minutes |
| Every 2 weeks | Profile session on A54 using Unity Profiler | 1 hour |
| Every 2 weeks | Review and clean up TODO comments in code | 30 minutes |
| Monthly | Dependency audit: check for Unity package updates | 30 minutes |
| Monthly | Backup full project to external drive or cloud (not just GitHub) | 15 minutes |
| Monthly | Playtest full mission start-to-finish as if you are a new player | 45 minutes |

Risk Register

These are the most likely things to derail this project. Read this page before each new phase.

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Disk full — Unity build fails | HIGH (already at 84.7%) | CRITICAL | Free 50 GB before Phase 1. Monitor weekly. |
| Mapbox SDK incompatible with Unity 6.3 | MEDIUM | HIGH | Check Mapbox GitHub issues before Phase 3. Have fallback: use OSM tiles directly via REST. |
| NVIDIA driver breaks desktop on Kali | MEDIUM | HIGH | Create Timeshift snapshot before driver install. Know how to boot to CLI and roll back. |
| Physics feels wrong and needs full rework | MEDIUM | HIGH | Allocate 3 extra weeks to Phase 2. Do not proceed until validation tests pass. |
| Performance on A54 never reaches 30 FPS | MEDIUM | HIGH | Profile early. Have a 'Lite mode' fallback: reduce AI, reduce weather particles, simpler map. |
| Tile streaming causes stuttering | MEDIUM | MEDIUM | Load tiles on background thread. Pre-load 2km ahead. Test at 100+ km/h. |
| Solo developer burnout | HIGH (18 months) | CRITICAL | Hard stop every Sunday. Do not work more than 25 hours/week on this. Celebrate milestones. |
| Scope creep — adding features not in GDD | HIGH | HIGH | Refer to GDD before adding anything new. New features go in a 'post-launch backlog'. |
| PlayFab free tier limits exceeded | LOW | MEDIUM | Monitor monthly active users. Free tier supports 1000 MAU — plenty for launch. |
| Apple App Store rejection | MEDIUM | MEDIUM | Read App Store review guidelines before submission. Privacy policy, data transparency are key. |
| OSM data missing for chosen city | LOW | MEDIUM | Verify OSM completeness at openstreetmap.org before choosing a city. Nairobi is well-mapped. |

Complete Tools & Resources Reference

Free Tools (Zero Cost)

| Tool | Purpose | Where to Get |
| --- | --- | --- |
| Unity 6.3 LTS | Game engine (already installed) | unityhub (already done) |
| VS Code | IDE (already installed) | Already configured |
| Mapbox Unity SDK | Real map streaming | mapbox.com/unity (free tier) |
| Overpass API | OSM road/route queries | overpass-api.de (no account needed) |
| OpenStreetMap | Map data source | openstreetmap.org |
| Git + Git LFS | Version control | sudo apt install git git-lfs |
| GitHub | Remote repository | github.com (free private repos) |
| PlayFab | Cloud save + leaderboards | playfab.microsoft.com (free tier) |
| Unity Gaming Services | Analytics + crash reporting | dashboard.unity3d.com |
| FMOD Studio | Audio engine | fmod.com (free for indie) |
| Blender | 3D modelling if needed | blender.org (completely free) |
| Overpass Turbo | Test OSM queries in browser | overpass-turbo.eu |
| ncdu | Disk usage analyser | sudo apt install ncdu |
| Android Debug Bridge | Deploy to phone | Included in Android SDK via Unity Hub |

Optional Paid Assets

| Asset | Cost | Purpose | Required? |
| --- | --- | --- | --- |
| NWH Vehicle Physics 2 | ~$90 | Advanced WheelCollider wrapper | Optional — saves 2–3 weeks |
| Mapbox Pro tier | $0–$500/mo | Higher API call limits | Only if 50k loads/mo exceeded |
| Apple Developer Program | $99/year | iOS App Store publishing | Required for iOS launch only |
| Google Play Developer | $25 one-time | Android publishing | Required for Play Store launch |
| Traffic Simulation Assets | $30–$80 | Pre-built AI traffic | Optional — speeds up Phase 5 |

Final Notes

This document is 18 months of your life compressed into pages. The most important rule is simple: finish each phase before starting the next. The biggest killer of solo game projects is jumping to the exciting parts before the foundations are solid.

The physics of a 12-tonne bus on real streets is genuinely interesting to get right. The first time you take a corner too fast on a wet road in Nairobi and feel the rear end step out — that is the moment this project becomes real. Every hour of foundation work in Phases 0–2 is building toward that moment.

You have good hardware for a solo developer, two excellent test devices, and a clear plan. Now execute it one checklist item at a time.

— End of Master Project Timeline —